|  | Closeout Report: Tablet Rollout` |
| --- | --- |

# Project Summary

Sauce & Spoon completed a tabletop tablet pilot in the bar areas of its North and Downtown locations. The pilot enabled guests to browse menus, place and customize orders, access promotions, and pay at the table. The project focused on improving the guest experience and restaurant operations while collecting data for a future expansion decision.

Baseline launch target: April 1 (beginning of Q2). Actual pilot launch: April 23. The 22-day variance followed a storm-related delay in upgraded tablet supply and implementation issues. The team used current-model tablets to proceed and preserved a future no-cost device-swap option.

# Methodology

Reviewed the project plan, launch milestones, shipment and implementation updates, stakeholder feedback, customer survey findings, and retrospective notes.

Compared the original baseline and quality standards with observed pilot findings and final post-improvement outcomes.

Used Agile Methodology

Results

Performance Baseline:

|  | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Actual Project Schedule vs Planned | Launch on Apr. 1 | Launched on Apr. 23 | We were able to launch on the day we wanted, but had to accelerate our tasks due to delays |
| Actual Project Cost vs Planned | Training materials and fees: $10,000 Hardware and software implementation across locations: $3,500 Maintenance (IT fees): $5,000 Updated website and menu design fee: $5,000 Other customization fees: $550 | Training materials and fees: $7,486 Hardware and software implementation across locations: $3,600 annually Maintenance (IT fees): $0 (included with hardware order subscription) Updated website and menu design fee: $4,250 Other customization fees: $578 | Overall, we nearly matched our budget |
| Planned Scope vs Delivered Scope | Install tablets at two restaurant locations Launch at the beginning of Q2 (April 1) Create a plan for how to train staff on the new system | Physically installed tablets at two restaurant locations via electrician Added menus, coupons, branding, and additional content to tablets Integrated tablets with POS system Negotiated with tablet vendor over timing Created a plan for training Managed waitstaff expectations and concerns Trained BOH and FOH Created system for maintenance/locking Implemented system of surveying and measuring customer satisfaction | We didn’t realize how many moving pieces we were going to encounter |

Key Accomplishments:

Installed tabletop tablets in the bar areas at both North and Downtown locations, including electrical work through an electrician.

Added menus, coupons, branding, and additional tablet content; integrated the tablets with the POS system.

Maintained the pilot schedule as closely as possible by selecting current-model tablets when upgraded models were delayed by storms.

Created and delivered training for front-of-house and back-of-house teams; addressed waitstaff expectations and concerns.

Implemented customer surveying and performance measurement, then used feedback to simplify tablet navigation and clarify payment options.

Introduced a pre-service testing checklist, helping reduce reported technical issues to below 5% weekly.

Met final targets for a 30-minute table-turn reduction and 25% food-waste reduction; Downtown exceeded the guest-count target with a 20% increase.

# Lessons Learned

- Conduct a pilot test before full implementation to identify issues early.

- Customer feedback is essential for validating the tablet ordering experience.

- User adoption cannot be assumed; customers may need guidance and support.

- Technical issues should be identified, tracked, and resolved quickly.

- Clear communication and staff support can improve customer adoption.

- Project success should be measured using both customer feedback and business KPIs.

- Continuous feedback helps identify improvements in tablet functionality, menu design, and ordering workflow.

# Next Steps

Continue operational monitoring of order accuracy and investigate sources of incorrect orders across the kitchen, FOH, and process flow.

Maintain the pre-service tablet checklist and the simplified navigation and payment messaging changes.

Strengthen cross-functional training and BOH readiness before considering a larger rollout.

Use pilot data, staffing readiness, costs, and customer experience findings to decide whether expansion beyond the bar areas is appropriate.

If upgraded tablets are deployed later, follow the vendor’s planned no-cost plug-swap process; no retraining was expected for that device change.

# Project Documentation Archive

- Project Charter

- Project Plan

- Stakeholder Analysis

- KPI Dashboard