## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration |  | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[5 empty] | Buffer |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Phase 1: Project Initiation and Scope setup
Review and finalize project charter | Ensure project objectives, scope, deliverables, and constraints are approved. |  |  | 2-3days |  | Peta
Conduct project kickoff meeting | Align stakeholders on project goals, responsibilities, and expectations. |  |  | 1 day |  | Peta
Confirm pilot location requirements | Gather requirements from North and Downtown locations for bar area deployment. |  |  | 2 days |  | Gilly & Alex
Plan pilot rollout activities | Outline launch milestones and operational safety |  |  | 2 days |  | Deanna / Peta
Milestone 1: project charter and pilot scope approved
Phase 2: Vendor Selection and Integration architecture
Define tablet project requirements | Document required features including ordering, payment, add-ons, coupons, and system compatibility. |  |  | 2 days |  | Peta
Research tablet vendors | Identify tablet solutions that meet project requirements. |  |  | 3-5 days |  | Seydou
Evaluate vendor capabilities and pricing | Review vendor features including POS/host integration, menu updates, add-ons, and coupons. |  |  | 3 days |  | Seydou
Select tablet vendor | Approve final vendor selection based on requirements. |  |  | 1 day |  | Deanna / peta
Order and receive tablets |  |  |  | 7 - 10 days |  | Seydou
Verify POS software version | If there is need of any update |  |  | 3 - 4 days |  | Gilly
Plan POS and host software integration | Plan software connections between new hardware and current POS |  |  | 1 day |  | Seydou
Finalize menu & coupon content |  |  |  | 2 - 5 days |  | Carter
Design tablet menu mock-ups & upload content | Ensure display matches Sauce & Spoon styling and features. |  |  | 3 - 4 hours |  | Graphic Designer / Peta
Milestone 2: Vendor Selected & Integration Technical Plan Approved
Phase 3: Hardware Deployment & Infrastructure
Define tablet installation requirements | Determine installation needs, including table wiring and setup requirements. |  |  | 2 days |  | Seydou / Peta
Comparing tablet pricing | To make sure they are in our budget |  |  |  |  | Peta
Coordinate installation requirements with vendor | Work with selected vendor to arrange installation details. |  |  | 3 days |  | Seydou / vendor techs
Plan pilot rollout activities | Coordinate preparation activities before pilot deployment. |  |  | 3 days |  | Peta
Install tablets at location |  |  |  | 2 days |  | Electrician
Milestone 3: Hardware Installed & System Integration Verified
Phase 4: Training, Testing & Pilot Launch
Pre training meeting to introduce tablets | Create resources for tablet usage and menu management training. |  |  | 1 day |  | Peta
Train small group of managers | Train managers on tablet operation |  |  |  |  | Seydou
Train restaurant employees | Train staff on tablet operation and updating menu items through the admin system. |  |  | 2 days |  | GM / Peta
Confirm staff readiness | Ensure restaurant teams are prepared before pilot launch. |  |  | 1 days |  | Gilly & Alex
Schedule staff meeting with the GM | To dicsuss anything that could affect waitstaff tips |  |  | 1 day |  | Peta / GM
Invite friends and family | To do a test run of tablets |  |  | 1 day |  | Peta / entire team
Test tablets before launch | To know if there is any issue |  |  | 1 day |  | Peta
Milestone 4: Staff Readiness Verified & Pilot Successfully Launched

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Confirm pilot location requirements | Establish needs for North & Downtown locations | 2 | 1 | 2 | 3 | H
Research & select tablet vendor | Compare vendor options and select Terrific Tablets | 4 | 3 | 4 | 5 | M
Order & receive tablets | Standard shipping takes 1 week; 2–3 day delay buffer | 7 | 5 | 7 | 10 | M
Verify POS software version | Check FlatPlate v3.0 requirement | 1 | 1 | 1 | 4 | M
Plan POS & software integration | Add code and reboot POS (takes a few hours) | 1 | 1 | 1 | 2 | H
Finalize menu & coupon content | Get discount values and menu list from Carter | 3 | 2 | 3 | 14 | L
Design menu mock-ups & upload | Create visuals and upload data to tablets | 2 | 1 | 2 | 4 | M
Install tablet hardware | Mount units and complete wiring setup | 3 | 2 | 3 | 5 | M
Train management & staff | Seydou trains managers; managers train waitstaff | 3 | 2 | 3 | 4 | H
Test tablets (Friends & Family) | Run live test event before official launch | 2 | 1 | 2 | 3 | H

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | Average ticket time: apps=8min; entrees=12-15min | How can we improve ticket times? | Ticket times | FALSE
Customer satisfaction | Check-out time: >1min | Are customers satisfied with checkout processes? | Customer satisfication | FALSE
Customer satisfaction | Technical issues: >5% reported | How can we improve customers' ability to use the tablets? | Technical issue reports | FALSE
Customer satisfaction | Order accuracy: 100% | Should we continue using the tablets? | Order accuracy for tablets vs servers | TRUE
Customer satisfaction | Wait time: >10min | How can we improve wait times for customers? | Reported wait times | FALSE
Customer satisfaction | Are customers having a better dining experience with the tablets? | Do we need to improve tablet features | Ease of use | TRUE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer satisfaction | During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Customer satisfaction | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
Customer satisfaction | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 - Lacking | 2 | 3 | 4 | 5 - Great
Customer satisfaction | How well did your waiter instruct you how to use the tablet? | Scaled | 1 - Not well | 2 | 3 - Very well
Customer satisfaction | On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 - Difficult | 2 | 3 | 4 | 5 - Easy
Customer satisfaction | On average, how long did you wait for your table? | Scaled | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Customer satisfaction | On average, how long did your dinner take? | Scaled | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min.
Customer satisfaction | Did the kitchen prepare your order correctly? | Yes/No | Yes | No | If no, what went wrong?
Customer satisfaction | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/false | TRUE | FALSE | If you don't agree with the above statement, why?
Customer satisfaction | How confident are you in submitting your payment through a tablet? | Scaled | 1 - Not at all | 2 | 3 | 4 | 5 - Very confident
Customer satisfaction | Did you sign up for the newsletter on the tablet? | Yes/No | Yes | No
Customer satisfaction | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | I liked the tablet experience better, and would like that going forward. | I would like a mix of tablet ordering at the table and waiter interaction. | I disliked the tablets, and would rather have a waiter. | I found both experiences comparable and it doesn't matter either way.
Customer satisfaction | Did you have any technical issues with your tablet? | Open-ended

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes