Project Charter: Tabletop Menu Tablets Pilot Launch

DATE: [25/07/26]

Project Summary

Sauce & Spoon is running a pilot project to test tabletop menu tablets at two locations: Downtown and North. Managed by Peta in coordination with Deanna (Director of Operations), Alex (Downtown GM), and Gilly (North GM), the project aims to speed up dining times, boost check averages, reduce food waste, and streamline overall operations. The pilot is set to launch in April, and we will track performance through the end of June to see if we should roll this out chain-wide.

Project Goals

- Cut table turn times by 30 minutes. (We dropped "reducing guest wait time" as a standalone goal since faster table turns naturally lower wait times). - Increase daily guest capacity: Bring in 10% more guests daily. - Decrease food waste by 25%. - Increase average check value from $65 to between $70 and $75 across locations through appetizer and specialty drink prompts. - Boost appetizer sales: Target an overall average appetizer sales increase of 15% across pilot stores: North (Gilly): Aim for a 10% increase. Downtown (Alex): Target a 20% increase. - Evaluation Window: Track and evaluate all project metrics from the April launch through the end of June (end of Q2).

Deliverables

- Fully installed tabletop tablets and integrated POS software at the Downtown and North locations. - Direct training and setup guides for servers, hosts, and kitchen staff. - A BOH monitoring plan to track kitchen ticket times and staff bandwidth during the pilot before making any payroll or hiring changes. - A post-pilot evaluation report compiled at the end of June summarizing sales, check averages, ticket times, and staff feedback.

Scope and Exclusion

In-Scope: - Installing hardware and software for the pilot at Downtown and North. - Testing features on the tablets that promote appetizers, specialty drinks, and coupon usage. - Training front-of-house and back-of-house teams on how to use the tablets. - Monitoring kitchen ticket times and staff workload during the pilot. - Tracking turn times, guest counts, and sales metrics from April through June. Out-of-Scope: - Installing tablets at any other Sauce & Spoon locations during this pilot phase. - Replacing or completely overhauling our primary POS hardware infrastructure. - Tracking "guest wait time" as an independent goal. - Reallocating front-of-house payroll or hiring new BOH staff (such as line cooks) prior to reviewing actual pilot performance and revenue data.

Benefits & Costs

Benefits: - Faster table turns mean we can seat more guests during peak hours without adding physical tables. - Raising the average check to $70–$75 adds direct revenue through drinks and appetizer upsells. - Cutting food waste by 25% saves money on food costs. - Gives leadership clear data on kitchen workload to determine if future BOH hiring is necessary. Costs: - Upfront costs for tablets, secure mounts, and charging stations. - Software licensing and integration setup fees. - Staff hours spent training on the new tech. - Potential added labour costs later if pilot data proves extra kitchen staff are required.

Appendix:

- Project Sponsor: Deanna (Director of Operations) - Project Manager: Peta - Key Team Members: Alex (Downtown GM), Gilly (North GM), Carter (Head Chef), Seyi (Senior Systems Analyst) - Timeline: Pilot goes live in April; performance metrics evaluated through the end of June