Project Charter: Tablet Rollout Pilot Project

DATE: [21/07/26]

Project Summary

Sauce & Spoon will implement a pilot rollout of tabletop menu tablets in the bar areas of two restaurant locations—Sauce & Spoon North and Sauce & Spoon Downtown. The pilot aims to improve operational efficiency, enhance the guest dining experience, reduce food waste, increase product mix, and increase restaurant revenue by allowing guests to browse the menu, place orders, customize meals, and pay directly from their tables. The planned pilot launch target is April 1 (beginning of Quarter 2); the actual pilot launch occurred April 23 after storm-related tablet shipment delays and implementation issues. The pilot will be monitored during Quarter 2, with performance evaluated at the end of Quarter 2 to determine whether a future rollout is justified.

Project Goals

- Reduce average table turn time by 30 minutes in the pilot locations. - Increase average daily guest count by 10%. - Reduce food waste by 25%. - Increase average check value from $65 to at least $75. - Increase appetizer sales by: 10% at Sauce & Spoon North 20% at Sauce & Spoon Downtown 15% overall across both locations - Increase product mix by promoting appetizers, specialty beverages, and coupons through the tablet system.

Deliverables

- Approved Project Charter. - Selected tablet vendor with menu recommendations, coupon functionality, and compatibility with the existing POS and host systems. - Fully installed tabletop menu tablets in the bar areas of Sauce & Spoon North and Downtown. - Integrated tablet system connected to the existing POS and host software. - Staff training materials and completed training for restaurant employees. - Successful pilot deployment of the tablet solution. - Pilot performance report evaluating project KPIs. - Final project closure report with recommendations for future rollout.

Benefits & Costs

Benefits - Faster table turnover and improved operational efficiency. - Improved guest dining experience through self-service ordering and payment. - Raising the average check to $70–$75 adds direct revenue through drinks and appetizer upsells. - Cutting food waste by 25% saves money on food costs. - Better order accuracy through direct guest-to-kitchen communication. - Data-driven insights to support future expansion decisions. Costs - Purchase of tabletop tablets and charging stations. - Tablet software licensing and vendor implementation costs. - Integration with POS and host systems. - Staff training and change management activities. - Project management and implementation resources. - Ongoing maintenance and technical support during the pilot.

Scope and Exclusion

In Scope - Pilot deployment in the bar areas of Sauce & Spoon North and Downtown. - Selection, procurement, installation, and configuration of tabletop tablets. - Integration with the existing POS and host software. - Menu customization, self-ordering, self-payment, menu recommendations, and coupon functionality. - Staff training and change management. - Monitoring project KPIs including: - Table turn time - Food waste - Average check value - Appetizer sales - Product mix - Daily guest count - Pilot evaluation through the end of Quarter 2. Scope Decision Update The pilot remains limited to the bar areas at North and Downtown. A request to expand to all dining sections was deferred because it would add tablets, wiring, staffing, operational risk, and schedule impact. Out of Scope - Company-wide rollout beyond the pilot locations. - Deployment outside the bar sections. - Replacement of the existing POS or host software. - Restaurant renovations or facility upgrades. - Menu redesign or pricing changes. - Company policy changes regarding guest meal returns or refunds. - Long-term staffing, payroll restructuring, or permanent hiring decisions. - Kitchen staff satisfaction initiatives unless approved through formal scope change.

Appendix:

### Key Stakeholders Deanna (Director of Operations): Project sponsor responsible for approval and strategic direction. Peta (Project Manager): Responsible for project planning, execution, and communication. Gilly and Alex (General Managers): Provide location-specific input and support pilot implementation. Carter (Executive Chef): Provides kitchen operations input and supports food waste reduction goals. Seydou (Restaurant Consultant): Supports tablet vendor research and selection. Restaurant Staff: Use the tablet system and participate in training. Key Assumptions - The tablet system will integrate with existing POS and host software. - Staff will complete training before the pilot launch. - Required tablet features, including add-ons and coupons, will be available. - Pilot results will be available for evaluation by the end of Quarter 2. ### Key Constraints - The pilot is limited to Sauce & Spoon North and Sauce & Spoon Downtown. - Tablets will only be deployed in the bar sections. - The project timeline is limited to Quarter 2 (April–June). - Policy changes and permanent staffing decisions are outside the project scope. Success Criteria - The project will be considered successful if it achieves: - 30-minute reduction in table turn time. - 25% reduction in food waste. - 10% increase in daily guest counts. - Average check value increase from $65 to $75. - 10% appetizer sales increase at North and 20% at Downtown. - Successful tablet implementation and operation during the pilot. Charter Update: - Baseline, Actual Launch & Post-Pilot Results - Baseline planned pilot launch: April 1 (beginning of Q2). Actual pilot launch: April 23. The 22-day variance followed storm-related delay of upgraded tablets and related implementation issues; the team used current-model tablets to protect the rollout. - Post-pilot improvements simplified tablet navigation, clarified card/cash payment messaging, strengthened staff pacing and training, and introduced a pre-service tablet testing checklist. - Final outcomes: table-turn time reduced by 30 minutes; daily guest count increased by 20% at Downtown; checkout time remained at one minute or less; technical issues fell below 5% weekly; and food waste reduced by 25%. - Order accuracy remained an operational improvement area.